## MAKENI ULTRASOUND
MAKENI GOVERNMENT HOSPITAL.
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NR 1
DEMOLITION
CEILING
A | Removing existing ceiling and noggins |  |  | Item
and cart away rubbish off site.
ELECTRICAL & MECHANICAL
B | Allow for removing all electrical and machanical fittings attached |  |  | Item
to the ceiling and walls to be demolished set aside for the client.
FINISHES
C | Allow for Scarifying floor and wall tiles and cart away rubbish |  |  | Item
off site. Ref to Toilet floor tiles
COMPONENT
D | Allow for removing existing doors and windows and set aside |  |  | Item
for the client
PLUMBING FITTINGS
E | Allow for the removal and carting away of the existing warn-out |  |  | Item
toilet fitting to pave way for new works
DEMOLITION
| Carried to Summary |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NR 2
ROOF
A | Allow for inspecting and making good defective roof covering |  |  | Item
sheet to prevent leak with specific reference to the Proposed
Ultrasound room and the rest part of the building.
ROOF
| Carried to summary |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NR.3
DOORS AND WINDOWS
Steel Door
A | Allow for making good existing steel casement door with locks | Nr | 1 |  | 0
and painting included overall sizes 900mm x 2100mmhigh.
Ref: to Ultrasound room
Steel Door
B | Allow for making good existing steel casement door with locks | Nr | 1 |  | 0
and painting included overall sizes 1800mm x 2100mmhigh.
Ref: to Main Ent.
WINDOWS
Existing Windows
Allow for making good existing steel casement windows to
include broken pane glasses, staple, hinges, mosquitoes mesh and
painting overall sizes:
C | 900 x 1200mm high. | Nr | 1 |  | 0
Ref: to Ultrasound room
D | Ditto to all other windows for the purpose of uniformity. |  |  | Item
DOORS AND WINDOWS :
| Carried to summary |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NR.4
FINISHES
The following are internally, unless otherwise
stated:
Floor finishings
A | Allow for making good floor finish as well as its associated |  |  | Item
skirting clean and maintain in good condition. Ref, Ultrasound room
Floor Tiles
Ceramic wall tiles
B | 450mm x 450mm x 6mm thick non-slip vitrified floor
| tiles laid on screeded bed | m2 | 4 |  | 0
(Ref: Toilets)
Cement Sand Screeded Backings
C | 38mm thick cement and sand (1:6 mix) screeded
| bed to receive floor tiles | m2 | 4 |  | 0
Wall finishings
Wall Tiles
Ceramic wall tiles
D | 300mm x 200mm x 6mm thick white glazed ceramic
| wall tiles fixed with matching colour cement slurry | m2 | 32 |  | 0
(Ref: Toilets)
Cement Sand Screeded Backings
F | 12mm thick cement and sand (1:6 mix) screeded
| bed to receive wall tiles | m2 | 32 |  | 0
Ceiling finishings
Internally
G | Suspended 200mm wide white colour PVC ceiling
| strips complete with all fixing accessories. | m2 | 18 |  | 0
Ref: to Ultrasound room & Toilets)
Noggins
H | 50mm x 50mm treated hardwood noggins to receive
| 600mm x 600mm hardboard ceilings. | m | 54 |  | 0
| To Collection |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
Painting and Decorating
Prepare and apply two undercoat and one finishing
coat emulsion paint on:
A | Rendered surfaces of wall | m2 | 45 |  | 0
Ref: to Ultrasound room
| Painting to Internal Wals | m2 | 295 |  | 0
Painting and Decorating
External Weather Shield paint
Prepare and apply two coat of high quality weather
shield paint on:
B | Rendered surfaces of wall | m2 | 146 |  | 0
Externally
| To Collection |  |  |  | 0
COLLECTIONS
| Page 9 |  |  |  | 0
| Page 10 |  |  |  | 0
FINISHES :
| Carried to summary |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NR.5
PLUMBING AND MECHANICAL INSTALLATION
Pipework, joint and support to the following cold
water and sanitary installation
Concealed uPVC service pipework to cold water and
sanitary installation including joints and supports to the
running lengths of the following:
A | P-trap WC suit complete with cistern | Nr | 2 |  | 0
B | Wash Hand Basin,single, with bottle trap 11/4'' | Nr | 2 |  | 0
C | Stainless floor drain | Nr | 2 |  | 0
SANITARY APPLIANCES
Suppy, assemble and fix the following:
D | Provide and install squat toilet of virtreos china or any other | Nr | 2 |  | 0
similar but approved fitting by the Project Manager.
E | Wash hand basin 520mm x 450mm including wall
| brackets, plugging and screwing to blockwork or | Nr | 2 |  | 0
concrete
F | 600mm long x 600mm wide silver floated mirror fixed | Nr | 2 |  | 0
with chromium plated dome headed screws to wall.
G | Chromium plated soap dish | Nr | 2 |  | 0
H | Chromium towel rail; 900mm long | Nr | 2 |  | 0
J | Chromium plated toilet roll holder | Nr | 2 |  | 0
K | Stainless Floor drain | Nr | 2 |  | 0
L | Allow the provisional sum of Le……………... for pipe
| ( soil and cold water pipes) fittings,and associated work |  |  | Sum
in plumbing installation
PLUMBING AND MECHANICAL INSTALLATION
| :Carried to Summary |  |  |  | 0
ITEM | DESCRICPTION | UNIT | QTY | RATE | AMOUNT
Le
ELEMENT NO. 6
ELECTRICAL INSTALLATIONS
Supply and install electrical "first Fix" for the
following generally in a conceled plastic conduit,
fittings includes chaseing , casting building in
conduits and sleeves through floors, walls and
ceiling plugged for fixing conduites and fitting
P V C boxex 3'' x 3''(3''x 6'')
A | AC Points | NR | 1 |  | 0
0
| Supply and install electrical "Second Fix" for the ground floor, |  |  |  | 0
| DRAW cable wire to circuts 6mm2 drwan in 25mm diameter |  |  |  | 0
| pvc conduits pipes wiring complete with all boxes and fittings |  |  |  | 0
| from distribution points to raw power A/C points outlets. |  |  |  | 0
B | Aircondiioners | NRS | 1 |  | 0
0
| FITTINGS AND ACCESSORIES |  |  |  | 0
| Provide and installed the followings for proper |  |  |  | 0
| offices and outdoor lighting luminaire |  |  |  | 0
C | Flourecent LED lighting fittings twin 2x600mm. | NRS | 2 |  | 0
0
D | Wheather shield big bulk head fittings with |  |  |  | 0
| enegy bulbs 18 watts day light | NRS | 4 |  | 0
0
E | Earthing Installation | NR | 1 |  | 0
0
F | 13 Amps double switche sockets for raw power | NRS | 1 |  | 0
0
G | 15 Amps Air conditioner units | NRS | 1 |  | 0
0
H | Supply, and install and terminate the following 415/240 V 50 HZ |  |  |  | 0
| 100 Amps 6 way TPN distribution boards. | NRS | 1 |  | 0
0
J | 10 amps light switches |  |  |  | 0
0
K | 1 gang 1 way switch | NRS | 3 |  | 0
0
L | Inverter ac units complete with connection accesserios |  |  |  | 0
| 12000btu | NRS | 1 |  | 0
0
M | Connect 25 mm dis x4 c pvc/swa/pvc amoured cable | Sum | 1 |  | 0
0
ELECTRICAL INSTALLATION
| :Carried to Summary |  |  |  | 0
PROPOSED REHABILITATION OF THE ULTRASOUND ROOM AT THE |  |  |  |  | AMOUNT
MAKENI GOVERNMENT HOSPITAL. |  |  |  |  | Le
SUMMARY
ELEMENT NR.1 REPAIRS
0
| ELEMENT NR.2 ROOF |  |  |  | 0
| ELEMENT NR.3 DOORS AND WINDOWS |  |  |  | 0
| ELEMENT NR.4 FINISHES |  |  |  | 0
| ELEMENT NR.5 PLUMBING & MECHANICAL |  |  |  | 0
INSTALLATION
| ELEMENT NR.6 ELECTRICAL INSTALLATION |  |  |  | 0
| SUB-TOTAL |  | Le |  | 0
ADD
| PRELIMINARIES 5% |  |  |  | 0
| TOTAL ESTIMATED COST:- |  | Le |  | 0